## Summary
CAPEX Summary
3k Factory - Munich
Overview expected Cash Out*
| 2026-02-01 | 2026-03-01 | 2026-04-01 | 2026-05-01 | 2026-06-01 | 2026-07-01 | 2026-08-01 | 2026-09-01 | 2026-10-01 | 2026-11-01 | 2026-12-01 | 2027-01-01 | 2027-02-01 | 2027-03-01 | 2027-04-01 | 2027-05-01 | 2027-06-01 | 2027-07-01 | 2027-08-01 | 2027-09-01 | 2027-10-01 | 2027-11-01 | 2027-12-01
Assembly Equipment
Testing
Logistics
Facility
Development Testrig
Others
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
*Incoming Invoice - payment terms might have up to 30days as payment target
Grafik für Steer Co etc.
Approved Budget
Stationen / Rubriken
- initial offer
- change cost
- expected cost to completion

## Data_Graphic_Assembly
| Budget | Spent | Approved | Cost of Completion
Assembly Equipment
Testing
Logistics
Facility
MRO
Machining Center
Prototyping
Battery Production
Total

## Assembly_Equipment
Detailed Costbook - Assembly Equipment |  |  | Delta | 124093.9
Supplier: xzy |  |  | Budget (2026 only) | 497250
|  |  | Cost of complection | 373156.1
Work Area / Station | Project Phase | Product | Description Cost Item | Amount [€] | Expected Cash Out | Cost Basis | Cost Driver | Basis Description | Assumptions | Approval Status | Approval Date | Zielanpassung | Comments / Notes / Links
Pre-Assembly I (Standplatz) |  |  |  | 87121.2
Pre-Assembly I (Standplatz) | Phase 1 | Bryan | Standard workbench with flexible Trolley | 25118.8 | 2026-06-01 | Initial Supplier Offer | Initial setup | 19238/93 |  | Submitted for Approval
Pre-Assembly I (Standplatz) | Phase 1 | Bryan | Kanban Trolley | 13434.4 | 2026-06-01 | Initial Supplier Offer | Initial setup | 19238/93 |  | Submitted for Approval
Pre-Assembly I (Standplatz) | Phase 1 | Bryan | Jigs & Fixtures (3d Print) - early Phase | 0 | 2026-07-01 | Initial Supplier Offer | Initial setup | see engineering workpackage |  | Submitted for Approval
Pre-Assembly I (Standplatz) | Phase 1 | Bryan | Decoupling Trolley large | 8568 | 2026-07-01 | Initial Supplier Offer | Initial setup | 19238/93 |  | Submitted for Approval
Pre-Assembly I (Standplatz) | Phase 1 | Bryan | Jigs & Fixtures - final version | 2000 | 2026-09-01 | Cost Estimation | Process
Pre-Assembly I (Standplatz)
Pre-Assembly I (Standplatz)
Pre-Assembly I (Standplatz)
Pre-Assembly I (Standplatz) | Phase 2 | Günther | Expansion Werkbenches | 18000 | 2026-09-01 | Cost Estimation |  |  |  | Pending Technical Clarification
Pre-Assembly I (Standplatz) | Phase 2 | Günther | Expansion Jigs & Fixtures (3d Print) - early Phase | 5000 | 2026-09-01 | Cost Estimation |  |  |  | Pending Technical Clarification
Pre-Assembly I (Standplatz) | Phase 2 | Günther | Expansion Trolleys | 5000 | 2026-09-01 | Cost Estimation |  |  |  | Pending Technical Clarification
Pre-Assembly I (Standplatz) | Phase 3 | Gin-Tonic | Produktintegration | 10000 | 2026-11-01 | Cost Estimation |  |  |  | Pending Technical Clarification
Pre-Assembly I (Standplatz)
Pre-Assembly I (Standplatz)
Pre-Assembly I (Standplatz)
Pre-Assembly II (takt) |  |  |  | 90077.4
Pre-Assembly II (takt) | Phase 1 | Bryan | Standard workbench with integrated Kanban | 16577.4 | 2026-06-01 | Initial Supplier Offer | Initial setup | 19238/93 |  | Pending Technical Clarification
Pre-Assembly II (takt) | Phase 1 | Bryan | Decoupling Trolley Small | 10500 | 2026-07-01 | Initial Supplier Offer | Initial setup | 19238/93
Pre-Assembly II (takt) | Phase 1 | Bryan | Jigs & Fixtures (3d Print) - early Phase | 0 | 2026-07-01 | Initial Supplier Offer | Initial setup | see engineering workpackage
Pre-Assembly II (takt) | Phase 1 | Bryan | Jigs & Fixtures - final version | 2000 | 2026-09-01 | Cost Estimation | Process
Pre-Assembly II (takt)
Pre-Assembly II (takt) | [9 empty] | Pending Technical Clarification
Pre-Assembly II (takt) | [9 empty] | Pending Technical Clarification
Pre-Assembly II (takt) | Phase 2 | Günther | Workbenches Bryan - Initial Setup | 36000 | 2026-06-01 | Cost Estimation | Initial setup |  |  | Pending Technical Clarification
Pre-Assembly II (takt) | Phase 2 | Günther | Jigs & Fixtures (3d Print) - early Phase | 10000 | 2026-07-01 | Cost Estimation | Initial setup |  |  | Pending Technical Clarification
Pre-Assembly II (takt) | Phase 2 | Günther | Trolleys | 5000 | 2026-07-01 | Cost Estimation | Initial setup
Pre-Assembly II (takt) | Phase 3 | Gin-Tonic | Produktintegration | 10000 | 2026-11-01 | Cost Estimation
Pre-Assembly II (takt)
Pre-Assembly II (takt)
Pre-Assembly II (takt)
Final Assembly |  |  |  | 133873
Final Assembly | Phase 1 | Bryan | Standard workbench with integrated Kanban | 27629 | 2026-06-01 | Initial Supplier Offer | Initial setup | 19238/93 |  | Pending Technical Clarification
Final Assembly | Phase 1 | Bryan | Jigs & Fixtures (3d Print) - early Phase | 0 | 2026-07-01 | Initial Supplier Offer | Initial setup | see engineering workpackage |  | Pending Technical Clarification
Final Assembly | Phase 1 | Bryan | Transport Trolley | 6244 | 2026-07-01 | Initial Supplier Offer | Initial setup | 19238/93 |  | Pending Technical Clarification
Final Assembly | Phase 1 | Bryan | Jigs & Fixtures - final version | 5000 | 2026-09-01 | Cost Estimation | Process
Final Assembly
Final Assembly | [9 empty] | Pending Technical Clarification
Final Assembly | [9 empty] | Pending Technical Clarification
Final Assembly | [9 empty] | Pending Technical Clarification
Final Assembly | Phase 2 | Günther | Workbenches Bryan - Initial Setup | 45000 | 2026-06-01 | Cost Estimation | Initial setup |  |  | Pending Technical Clarification
Final Assembly | Phase 2 | Günther | Jigs & Fixtures (3d Print) - early Phase | 20000 | 2026-07-01 | Cost Estimation | Initial setup
Final Assembly | Phase 2 | Günther | Trolleys | 20000 | 2026-07-01 | Cost Estimation | Initial setup
Final Assembly | Phase 3 | Gin-Tonic | Produktintegration | 10000 | 2026-11-01 | Cost Estimation
Final Assembly
Final Assembly
Final Assembly
Rework Area / Special workbench |  |  |  | 19756
Rework Area / Special workbench | Phase 1 | Bryan | Workbenches Bryan - Initial Setup | 14756 | 2026-06-01 | Cost Estimation | Initial setup
Rework Area / Special workbench | Phase 1 | Bryan | Jigs & Fixtures (3d Print) - early Phase | 0 | 2026-07-01 | Initial Supplier Offer | Initial setup | see engineering workpackage
Rework Area / Special workbench | Phase 1 | Bryan | Jigs & Fixtures - final version | 5000 | 2026-09-01 | Cost Estimation | Process
Rework Area / Special workbench
Rework Area / Special workbench
Rework Area / Special workbench
Rework Area / Special workbench
Rework Area / Special workbench
Rework Area / Special workbench
Rework Area / Special workbench
Tools / Jigs / Fixtures |  |  |  | 0
Tools / Jigs / Fixtures | Phase 1 | Bryan | Bryan - Pre Assembly I - initial setup
Tools / Jigs / Fixtures | Phase 1 | Bryan | Bryan - Pre Assembly II - initial setup
Tools / Jigs / Fixtures | Phase 1 | Bryan | Bryan - Final Assembly - initial setup
Tools / Jigs / Fixtures
Tools / Jigs / Fixtures
Tools / Jigs / Fixtures
Tools / Jigs / Fixtures
Tools / Jigs / Fixtures
Tools / Jigs / Fixtures
Tools / Jigs / Fixtures
Decoupling / Conveyor |  |  |  | 0
Decoupling / Conveyor | Phase 1 | Bryan | WPC Final assembly line
Decoupling / Conveyor | Phase 1 | Bryan | Conveyor Final assembly line
Decoupling / Conveyor | Phase 1 | Bryan | WPC Pre-Assembly II
Decoupling / Conveyor | Phase 1 | Bryan | Conveyor Pre-Assembly II
Decoupling / Conveyor
Decoupling / Conveyor
Decoupling / Conveyor | Phase 2 | Günther | WPC Final assembly line
Decoupling / Conveyor | Phase 2 | Günther | Conveyor Final assembly line
Decoupling / Conveyor | Phase 2 | Günther | WPC Pre-Assembly II
Decoupling / Conveyor | Phase 2 | Günther | Conveyor Pre-Assembly II
Decoupling / Conveyor | Phase 3 | Gin-Tonic | WPC Final assembly line
Decoupling / Conveyor | Phase 3 | Gin-Tonic | Conveyor Final assembly line
Decoupling / Conveyor | Phase 3 | Gin-Tonic | WPC Pre-Assembly II
Decoupling / Conveyor | Phase 3 | Gin-Tonic | Conveyor Pre-Assembly II
Decoupling / Conveyor
Decoupling / Conveyor | Phase 1 | Bryan | Foam Inlet Decoupling Racks
Decoupling / Conveyor | Phase 2 | Günther | Foam Inlet Decoupling Racks
Decoupling / Conveyor | Phase 3 | Gin-Tonic | Foam Inlet Decoupling Racks
Additional / Diverses |  |  |  | 42328.5
Additional / Diverses | Phase 1 | Bryan | Konstruktion und Projektierung | 8960
Additional / Diverses | Phase 1 | Bryan | Assembly and Transport Assembly Equipment | 27968.5
Additional / Diverses | Phase 1 | Bryan | Engineering hours jigs and fixtures and detailed design phase | 5400
Additional / Diverses
Additional / Diverses
Additional / Diverses
Additional / Diverses | Phase 1 | Bryan | Scanner - ZEBRA (25x)
Additional / Diverses | Phase 1 | Bryan | Tabletts / PC
Additional / Diverses
Additional / Diverses
Additional / Diverses
Additional / Diverses
Additional / Diverses

## Testing
Detailed Costbook - Assembly Equipment |  |  | Delta | 723314
Supplier: xzy |  |  | Budget (2026 only) | 769250
|  |  | Cost of complection | 45936
Work Area / Station | Project Phase | Product | Description Cost Item | Amount [€] | Expected Cash Out | Cost Basis | Cost Driver | Basis Description | Assumptions | Approval Status | Approval Date | Comments / Notes / Links
Pre-Development |  |  |  | 45936
Pre-Development | Phase 1 | Bryan | Pre-Development with company Aumann | 45936
Station 1 |  |  |  | 0
Station 2 |  |  |  | 0
Station 3 |  |  |  | 0
Peripherie |  |  |  | 0
Note on E3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Just initial setup and wihtout Development

## Logistics
Detailed Costbook - Assembly Equipment |  |  | Delta | 221000
Supplier: xzy |  |  | Budget (2026 only) | 221000
|  |  | Cost of complection | 0
Work Area / Station | Project Phase | Product | Description Cost Item | Amount [€] | Expected Cash Out | Cost Basis | Cost Driver | Basis Description | Assumptions | Approval Status | Approval Date | Comments / Notes / Links
Incoming Inspection
KLT / GLT
FTS / Transport
Racking Solution
|  |  | Lift System | 80000 | 2026-07-01 | Cost Estimation
Note on E3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Just initial setup and wihtout Development

## Facility
Detailed Costbook - Assembly Equipment
Supplier: xzy
0
Work Area / Station | Project Phase | Product | Description Cost Item | Amount [€] | Expected Cash Out | Cost Basis | Cost Driver | Basis Description | Assumptions | Approval Status | Approval Date | Comments / Notes / Links
Bauliche Veränderung
Media connection
Floor
|  |  | ESD Floor | 50966.83 | 2026-05-01 | Initial Supplier Offer | Initial setup | Landshuter Industrieboden | 916,7 sqm (production + MRO) | Approved by Steering Committee | 2025-03-10 | Approved by Nemo via Email
Fence / Safety

## Prototyping
Detailed Costbook - Assembly Equipment
Supplier: xzy
0
Work Area / Station | Project Phase | Product | Description Cost Item | Amount [€] | Expected Cash Out | Cost Basis | Cost Driver | Basis Description | Assumptions | Approval Status | Approval Date | Comments / Notes / Links

## 2027_FC
Detailed Costbook - Assembly Equipment
Supplier: xzy
0
Work Area / Station | Project Phase | Product | Description Cost Item | Amount [€] | Expected Cash Out | Cost Basis | Cost Driver | Basis Description | Assumptions | Approval Status | Approval Date | Comments / Notes / Links

## Dropdown
Cost Basis | Status | Project Phase |  | Product | Expected Cash Out
Cost Estimation | Open | Phase 1 | Initial Production Start Bryan | Bryan | 2026-02-01
Initial Supplier Offer | Submitted for Approval | Phase 2 | Ramp-Up / Integration Günther | Günther | 2026-03-01
Revised Supplier Offer | Approved by Steering Committee | Phase 3 | Output Increase / Optimization | Gin-Tonic | 2026-04-01
Change Cost | Rejected | Phase 4 | Automation / max. Capa | Overall | 2026-05-01
| On Hold |  |  |  | 2026-06-01
| Pending Supplier Negotiation |  |  |  | 2026-07-01
| Pending Technical Clarification |  |  |  | 2026-08-01
| Obsolete |  |  |  | 2026-09-01
2026-10-01
Basis Description (Helpfull Phrases) |  |  |  |  | 2026-11-01
Based on supplier offer Date / Numer |  |  |  |  | 2026-12-01
Derived from Change Request [CR_xx001] |  |  |  |  | 2027-01-01
Based on reference project |  |  |  |  | 2027-02-01
Supplier quotation not yet available |  |  |  |  | 2027-03-01
Estimated using … (e.g. cycle time, volume…) |  |  |  |  | 2027-04-01
2027-05-01
2027-06-01
2027-07-01
Cost Driver |  |  |  |  | 2027-08-01
Product |  |  |  |  | 2027-09-01
Process |  |  |  |  | 2027-10-01
New requirements assembly |  |  |  |  | 2027-11-01
New requirements testing |  |  |  |  | 2027-12-01
Initial setup

## BudgetTemplate19.02.2026
[15 empty] | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2027 | 2027 | 2027 | 2027 | 2027 | 2027 | 2027 | 2027 | 2027 | 2027 | 2027 | 2027 | 2028 | 2028 | 2028 | 2028 | 2028 | 2028 | 2028 | 2028 | 2028 | 2028 | 2028 | 2028 | 2029 | 2029 | 2029 | 2029 | 2029 | 2029 | 2029 | 2029 | 2029 | 2029 | 2029 | 2029 | 2030 | 2030 | 2030 | 2030 | 2030 | 2030 | 2030 | 2030 | 2030 | 2030 | 2030 | 2030 |  |  |  | 2025 | 2026 | 2026 | 2026 | 2026 | 2027 | 2027 | 2027 | 2027 | 2028 | 2028 | 2028 | 2028 | 2029 | 2029 | 2029 | 2029 | 2030 | 2030 | 2030 | 2030
[15 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
[15 empty] | Q1 2025 | Q1 2025 | Q1 2025 | Q2 2025 | Q2 2025 | Q2 2025 | Q3 2025 | Q3 2025 | Q3 2025 | Q4 2025 | Q4 2025 | Q4 2025 | Q1 2026 | Q1 2026 | Q1 2026 | Q2 2026 | Q2 2026 | Q2 2026 | Q3 2026 | Q3 2026 | Q3 2026 | Q4 2026 | Q4 2026 | Q4 2026 | Q1 2027 | Q1 2027 | Q1 2027 | Q2 2027 | Q2 2027 | Q2 2027 | Q3 2027 | Q3 2027 | Q3 2027 | Q4 2027 | Q4 2027 | Q4 2027 | Q1 2028 | Q1 2028 | Q1 2028 | Q2 2028 | Q2 2028 | Q2 2028 | Q3 2028 | Q3 2028 | Q3 2028 | Q4 2028 | Q4 2028 | Q4 2028 | Q1 2029 | Q1 2029 | Q1 2029 | Q2 2029 | Q2 2029 | Q2 2029 | Q3 2029 | Q3 2029 | Q3 2029 | Q4 2029 | Q4 2029 | Q4 2029 | Q1 2030 | Q1 2030 | Q1 2030 | Q2 2030 | Q2 2030 | Q2 2030 | Q3 2030 | Q3 2030 | Q3 2030 | Q4 2030 | Q4 2030 | Q4 2030
TYTAN Technologies
[10 empty] | CAPITAL EXPENSES | [79 empty] | Q4 2025 | Q1 2026 | Q2 2026 | Q3 2026 | Q4 2026 | Q1 2027 | Q2 2027 | Q3 2027 | Q4 2027 | Q1 2028 | Q2 2028 | Q3 2028 | Q4 2028 | Q1 2029 | Q2 2029 | Q3 2029 | Q4 2029 | Q1 2030 | Q2 2030 | Q3 2030 | Q4 2030 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | time axis 2025-01-01 to 2030-12-01
1 | Identifier | Account | Account name | Category | CC | CC name | Ccar | Ccar name | category | Description | Date | Unit Cost | Useful Life (months) | Until
2 | CAPEX | 40000 | technical equipment and machinery | CAPEX | 4800 | 4800 - Manfuacturing Equipment and Tools | I0001 | I0001 - Office Move Moander |  | Ausstattung Prototyping | 2026-01-01 | 120000 | 120 | 2035-12-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 0 | 0 | 0 | 0
3 | CAPEX | 40000 | technical equipment and machinery | CAPEX | 4800 | 4800 - Manfuacturing Equipment and Tools | I0001 | I0001 - Office Move Moander |  | Ausstattung Prototyping Tools | 2025-12-01 | 250000 | 36 | 2028-11-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250000 | 0 | 0 | 0 | 0 | 0
4 | CAPEX |  |  |  | 4800 | 4800 - Manfuacturing Equipment and Tools | M9000 | M9000 - Production Equipment & Machines | Facility | ESD Floor | 2025-05-01 | 129000 | 120 | 2035-04-01 | 0 | 0 | 0 | 0 | 129000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 129000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | CAPEX |  |  |  | 4800 | 4800 - Manfuacturing Equipment and Tools | M9000 | M9000 - Production Equipment & Machines |  | Electrical Workshop | 2026-09-01 | 120000 | 120 | 2036-08-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 0 | 0 | 0 | 0
6 | CAPEX | 40000 | technical equipment and machinery | CAPEX | 4800 | 4800 - Manfuacturing Equipment and Tools | M9000 | M9000 - Production Equipment & Machines |  | Launcher Production | 2026-06-01 | 40000 | 120 | 2036-05-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000 | 0 | 0 | 0 | 0
7 | CAPEX | 40000 | technical equipment and machinery | CAPEX | 4800 | 4800 - Manfuacturing Equipment and Tools | M9000 | M9000 - Production Equipment & Machines |  | Car / Van - Workshop | 2026-09-01 | 60000 | 120 | 2036-08-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60000 | 0 | 0 | 0 | 0
8 | CAPEX | 40000 | technical equipment and machinery | CAPEX | 4800 | 4800 - Manfuacturing Equipment and Tools | M9000 | M9000 - Production Equipment & Machines |  | Ground Control Test Station | 2026-06-01 | 40000 | 120 | 2036-05-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000 | 0 | 0 | 0 | 0
9 | CAPEX | 40000 | technical equipment and machinery | CAPEX | 4800 | 4800 - Manfuacturing Equipment and Tools | M9000 | M9000 - Production Equipment & Machines |  | Metal Workshop | 2026-09-01 | 200000 | 120 | 2036-08-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 0 | 0 | 0 | 0
10 | CAPEX | 40000 | technical equipment and machinery | CAPEX | 4800 | 4800 - Manfuacturing Equipment and Tools | M9000 | M9000 - Production Equipment & Machines | Assembly Equipment | Equipment for Line 3 - 2027 | 2027-04-01 | 700000 | 120 | 2037-03-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 700000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 700000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 700000 | 0 | 0 | 0
11 | CAPEX | 40000 | technical equipment and machinery | CAPEX | 4400 | 4400 - Logistics | M9000 | M9000 - Production Equipment & Machines | Battery Production / Others | Battery Storrage | 2026-07-01 | 80000 | 120 | 2036-06-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80000 | 0 | 0 | 0 | 0
12 | CAPEX | 40000 | technical equipment and machinery | CAPEX | 4800 | 4800 - Manfuacturing Equipment and Tools | M9000 | M9000 - Production Equipment & Machines | Battery Production / Others | Battery Pack Production - Equipment | 2026-07-01 | 765000 | 120 | 2036-06-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 765000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 765000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 765000 | 0 | 0 | 0 | 0
13 | CAPEX | 40000 | technical equipment and machinery | CAPEX | 4800 | 4800 - Manfuacturing Equipment and Tools | M9000 | M9000 - Production Equipment & Machines | Battery Production / Others | Battery Pack Production - Room | 2026-07-01 | 120000 | 120 | 2036-06-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 0 | 0 | 0 | 0
14 | CAPEX | 40000 | technical equipment and machinery | CAPEX | 4000 | 4000 - Operations | M2000 | M2000 - Operations car pool |  | Service Car | 2026-02-01 | 50000 | 60 | 2031-01-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 0 | 0 | 0 | 0
15 | CAPEX | 40000 | technical equipment and machinery | CAPEX | 4000 | 4000 - Operations | M2000 | M2000 - Operations car pool |  | Transport / Van | 2026-02-01 | 100000 | 60 | 2031-01-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 0
16 | CAPEX | 40000 | technical equipment and machinery | CAPEX | 4700 | 4700 - Prototyping | M9000 | M9000 - Production Equipment & Machines |  | Equipment for new manufacturing Processes H1 | 2026-05-01 | 150000 | 120 | 2036-04-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 0 | 0 | 0 | 0
17 | CAPEX | 40000 | technical equipment and machinery | CAPEX | 4000 | 4000 - Operations | I0006 | I0006 - ISO 27001 Security Program | Facility | Safety and Security Installation | 2026-04-01 | 303000 | 120 | 2036-03-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 303000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 303000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 303000 | 0 | 0 | 0 | 0
18 | CAPEX | 40000 | technical equipment and machinery | CAPEX | 4000 | 4000 - Operations | I0002 | I0002 - Office Expansion |  | Office & Visitor Space | 2026-04-01 | 124000 | 120 | 2036-03-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 124000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 124000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 124000 | 0 | 0 | 0 | 0
19 | CAPEX | 40000 | technical equipment and machinery | CAPEX | 4400 | 4400 - Logistics | M9000 | M9000 - Production Equipment & Machines | Logistics | Equipment Q2 | 2026-05-01 | 140000 | 120 | 2036-04-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 140000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 140000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 140000 | 0 | 0 | 0 | 0
20 | CAPEX | 40000 | technical equipment and machinery | CAPEX | 4400 | 4400 - Logistics | M9000 | M9000 - Production Equipment & Machines | Logistics | Equipment Q3 | 2026-09-01 | 80000 | 120 | 2036-08-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80000 | 0 | 0 | 0 | 0
21 | CAPEX | 40000 | technical equipment and machinery | CAPEX | 4400 | 4400 - Logistics | M9000 | M9000 - Production Equipment & Machines | Logistics | Equipment Q4 | 2026-11-01 | 40000 | 120 | 2036-10-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000 | 0 | 0 | 0 | 0
22 | CAPEX | 40000 | technical equipment and machinery | CAPEX | 4800 | 4800 - Manfuacturing Equipment and Tools | M9002 | M9002 - Production Equipment & Machines Line 1 | Testing | End of Line Test Station Line 1 Start | 2026-03-01 | 217500 | 120 | 2036-02-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 217500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 217500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 217500 | 0 | 0 | 0 | 0
[6 empty] | 4800 - Manfuacturing Equipment and Tools | M9002 | M9002 - Production Equipment & Machines Line 1 | Testing | End of Line Test Station Line 1 FAT | 2026-06-01 | 362500 | 120 | 2036-05-01 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 362500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 362500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 362500 | 0 | 0 | 0 | 0
[6 empty] | 4800 - Manfuacturing Equipment and Tools | M9002 | M9002 - Production Equipment & Machines Line 1 | Testing | End of Line Test Station Line 1 SAT | 2026-06-01 | 145000 | 120 | 2036-05-01 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 145000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 145000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 145000 | 0 | 0 | 0 | 0
23 | CAPEX | 40000 | technical equipment and machinery | CAPEX | 4000 | 4000 - Operations | I0002 | I0002 - Office Expansion | Facility | Office & Visitor Space | 2026-06-01 | 98000 | 120 | 2036-05-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 98000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 98000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 98000 | 0 | 0 | 0 | 0
24 | CAPEX | 40000 | technical equipment and machinery | CAPEX | 4000 | 4000 - Operations | I0002 | I0002 - Office Expansion |  | Office 3 | 2026-09-01 | 150000 | 120 | 2036-08-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 0 | 0 | 0 | 0
23 | CAPEX | 40000 | technical equipment and machinery | CAPEX | 4800 | 4800 - Manfuacturing Equipment and Tools | M9002 | M9002 - Production Equipment & Machines Line 1 | Assembly Equipment | Automation Equipment 2027 | 2027-03-01 | 250000 | 120 | 2037-02-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250000 | 0 | 0 | 0
24 | CAPEX | 40000 | technical equipment and machinery | CAPEX | 4800 | 4800 - Manfuacturing Equipment and Tools | M9003 | M9003 - Production Equipment & Machines Line 2 | Testing | End of Line Test Station Line 2 Start | 2026-10-01 | 180000 | 120 | 2036-09-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 180000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 180000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 180000 | 0 | 0 | 0 | 0
[6 empty] | 4800 - Manfuacturing Equipment and Tools | M9003 | M9003 - Production Equipment & Machines Line 2 | Testing | End of Line Test Station Line 2 FAT | 2027-02-01 | 300000 | 120 | 2037-01-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000 | 0 | 0 | 0
[6 empty] | 4800 - Manfuacturing Equipment and Tools | M9003 | M9003 - Production Equipment & Machines Line 2 | Testing | End of Line Test Station Line 2 SAT | 2027-03-01 | 120000 | 120 | 2037-02-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 0 | 0 | 0
25 | CAPEX | 40000 | technical equipment and machinery | CAPEX | 4700 | 4700 - Prototyping | M9000 | M9000 - Production Equipment & Machines |  | Equipment for new manufacturing Processes H2 | 2026-09-01 | 400000 | 36 | 2029-08-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 0 | 0 | 0 | 0
26 | CAPEX | 40000 | technical equipment and machinery | CAPEX | 4000 | 4000 - Operations | I0002 | I0002 - Office Expansion |  | Kitchens (5 in total) | 2026-05-01 | 90000 | 36 | 2029-04-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90000 | 0 | 0 | 0 | 0
25 | CAPEX | 40000 | technical equipment and machinery | CAPEX | 4800 | 4800 - Manfuacturing Equipment and Tools | M9003 | M9003 - Production Equipment & Machines Line 2 | Assembly Equipment | Automation Equipment Line 2 | 2026-10-01 | 200000 | 120 | 2036-09-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 0 | 0 | 0 | 0
26 | CAPEX | 40000 | technical equipment and machinery | CAPEX | 4800 | 4800 - Manfuacturing Equipment and Tools | M9000 | M9000 - Production Equipment & Machines | MRO | Equipment MRO Line | 2026-08-01 | 500000 | 120 | 2036-07-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 0 | 0 | 0 | 0
27 | CAPEX | 40000 | technical equipment and machinery | CAPEX | 4800 | 4800 - Manfuacturing Equipment and Tools | M9002 | M9002 - Production Equipment & Machines Line 1 | Assembly Equipment | Manfacturing Equipment and Tools Phase 1 | 2026-03-01 | 105000 | 36 | 2029-02-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 105000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 105000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 105000 | 0 | 0 | 0 | 0
28 | CAPEX | 40000 | technical equipment and machinery | CAPEX | 4800 | 4800 - Manfuacturing Equipment and Tools | M9002 | M9002 - Production Equipment & Machines Line 1 | Assembly Equipment | Manfacturing Equipment and Tools Phase 1 | 2026-06-01 | 87500 | 36 | 2029-05-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 87500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 87500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 87500 | 0 | 0 | 0 | 0
29 | CAPEX | 40000 | technical equipment and machinery | CAPEX | 4800 | 4800 - Manfuacturing Equipment and Tools | M9003 | M9003 - Production Equipment & Machines Line 2 | Assembly Equipment | Manfacturing Equipment and Tools Phase 2 | 2026-06-01 | 105000 | 36 | 2029-05-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 105000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 105000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 105000 | 0 | 0 | 0 | 0
30 | CAPEX | 40000 | technical equipment and machinery | CAPEX | 4800 | 4800 - Manfuacturing Equipment and Tools | M9003 | M9003 - Production Equipment & Machines Line 2 | Assembly Equipment | Manfacturing Equipment and Tools Phase 2 | 2026-10-01 | 87500 | 36 | 2029-09-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 87500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 87500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 87500 | 0 | 0 | 0 | 0
31 | CAPEX | 40000 | technical equipment and machinery | CAPEX | 4800 | 4800 - Manfuacturing Equipment and Tools | M9000 | M9000 - Production Equipment & Machines | MRO | MRO Equipment and Tools | 2026-08-01 | 105000 | 120 | 2036-07-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 105000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 105000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 105000 | 0 | 0 | 0 | 0
32 | CAPEX |  |  |  | 4700 | 4700 - Prototyping | M9000 | M9000 - Production Equipment & Machines | Prototyping | Development Test Equipment | 2026-07-01 | 150000 | 120 | 2036-06-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 0 | 0 | 0 | 0
33 | CAPEX |  |  |  | 4700 | 4700 - Prototyping | M9000 | M9000 - Production Equipment & Machines | Prototyping | Development Test Equipment | 2026-10-01 | 150000 | 120 | 2036-09-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 0 | 0 | 0 | 0
34 | CAPEX |  |  |  | 4700 | 4700 - Prototyping | M9000 | M9000 - Production Equipment & Machines | Prototyping | Development Test Equipment | 2026-12-01 | 150000 | 120 | 2036-11-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 0 | 0 | 0 | 0
35 | CAPEX | 40000 | technical equipment and machinery | CAPEX | 4000 | 4000 - Operations | M3000 | M3000 - Facility Management 3k factory | Facility | Initial Construction Cost Q1 | 2026-03-01 | 150000 | 120 | 2036-02-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 0 | 0 | 0 | 0
36 | CAPEX | 40000 | technical equipment and machinery | CAPEX | 4000 | 4000 - Operations | M3000 | M3000 - Facility Management 3k factory | Facility | Initial Construction Cost Q2 | 2026-06-01 | 200000 | 120 | 2036-05-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 0 | 0 | 0 | 0
37 | CAPEX | 40000 | technical equipment and machinery | CAPEX | 4000 | 4000 - Operations | M3000 | M3000 - Facility Management 3k factory | Facility | Initial Construction Cost Q3 | 2026-10-01 | 100000 | 120 | 2036-09-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 0
38 | CAPEX | 40000 | technical equipment and machinery | CAPEX | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[95 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[10 empty] | Total Capex |  |  |  |  | 0 | 0 | 0 | 0 | 129000 | 0 | 0 | 0 | 0 | 0 | 0 | 250000 | 120000 | 150000 | 472500 | 427000 | 380000 | 1078000 | 1115000 | 605000 | 1010000 | 717500 | 40000 | 150000 | 0 | 300000 | 370000 | 700000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 129000 | 0 | 250000 | 742500 | 1885000 | 2730000 | 907500 | 670000 | 700000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250000 | 6265000 | 1370000 | 0 | 0 | 0
Formulas:
Until = IF([Date]="","",EDATE([Date],[Useful Life (months)]-1))
Note on N7: assume 36 months for simplicity's sake. Actual depreciation for tax purposes may vary.
Note on K41: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Equipment Bryan
Note on K43: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Integration Günther + Gin Tonic